CISC7204  DATA VISUALIZATION

Assignment 02 Pair Project Proposal

Post-Pandemic Tourism Recovery: Comparing Arrivals and Receipts Across World Regions

Revised proposal prepared from the Proposal Ideation and Project Proposal Guideline.

| Course code | CISC7204 |
| --- | --- |
| Course title | Data Visualization |
| Coursework item | Assignment 02 — Pair Project Proposal |
| Pair number | Pair 10 |
| Pair member 1 | He Kejia— Student ID: MC664602 |
| Pair member 2 | Dong Yushuo— Student ID: MC664934 |
| Submission date | 24 October 2026 |

Central research question

Between 2019 and the latest year with comparable country-level coverage, how does the recovery of international tourist arrivals compare with the recovery of international tourism receipts across World Bank regions?

This revised proposal defines a two-person data visualization project that compares the post-pandemic recovery of tourist volume and tourism earnings. It states the research question, project purpose, datasets, tasks, success criteria, collaboration arrangements, and deliverables needed to complete the work within the assignment period.

1. Project Title and Research Question

Project title

Uneven Recovery: Comparing Tourist Arrivals and Tourism Receipts After COVID-19

Research question

Between 2019 and the latest year with comparable country-level coverage, how does the recovery of international tourist arrivals compare with the recovery of international tourism receipts across World Bank regions, and which regions show the largest gap between the two recovery rates?

Region and domain category

Region: Global, with comparisons across World Bank regions.

Domain: Tourism and economic development.

Period: 2019 is the pre-pandemic baseline. The comparison year will be the latest year with at least 60% valid country coverage for both indicators; the same matched sample of countries will be used for both recovery measures.

2. Project Purpose

Outcomes

The project connects the course learning outcomes by integrating public-data acquisition, cleaning, exploratory analysis, static visualization, interactive dashboard development, and evidence-based communication. It also builds practical experience relevant to future study and careers in data science, analytics, and visual communication.

Skills

Retrieving and documenting public data from the World Bank API.

Cleaning, reshaping, joining, and validating country-level datasets with Python and pandas.

Handling missing values, regional aggregates, and unmatched observations.

Creating static charts with Matplotlib or Seaborn and interactive views with Plotly and Dash.

Communicating data quality, uncertainty, limitations, and conclusions clearly.

Knowledge

Recovery-index construction and matched-sample comparison.

Regional aggregation and cross-country analysis.

The analytical difference between tourist volume and tourism receipts.

Visual encoding choices, dashboard filtering, and reproducibility.

The distinction between association and causation.

3. Project Tasks and Work Plan

Both members will contribute to the analytical decisions and review each other’s work. Primary responsibility is divided as shown below.

| Task | Specific work | Lead | Deliverable |
| --- | --- | --- | --- |
| 1. Scope and data dictionary | Define indicator codes, baseline year, comparison-year rule, inclusion criteria, and the recovery-index formula. | Both | Scope note and data dictionary |
| 2. Data acquisition | Download arrivals, receipts, and country metadata; record source URLs, access date, and raw-file details. | Kejia | Raw data and source log |
| 3. Cleaning and validation | Reshape the data, standardise country codes, remove regional aggregates, and document missing-value decisions. | Kejia | Clean dataset and cleaning notes |
| 4. Recovery analysis | Compute country and regional recovery indices; calculate the gap between receipts and arrivals recovery. | Both | Analysis-ready dataset and summary tables |
| 5. Static visualizations | Create a time-series line chart, regional grouped bar chart, and country-level scatter plot with clear annotations. | Yushuo | Publication-quality figures |
| 6. Interactive dashboard | Build Plotly/Dash views with region and income-group filters, a country table, and source notes. | Yushuo | Working dashboard and screenshot |
| 7. Interpretation and QA | Answer the research question, explain limitations, verify calculations, and check reproducibility. | Both | Interpretation and QA checklist |
| 8. Submission package | Assemble the notebook, README, supporting files, and correctly named submission files. | Both | Final submission package |

4. Available Datasets

The project will use the following public datasets. All are tabular or API-accessible and can be downloaded reproducibly.

| Dataset | Use in the project | Link |
| --- | --- | --- |
| International tourism, number of arrivals (ST.INT.ARVL) | World Bank — annual country-level arrivals | https://data.worldbank.org/indicator/ST.INT.ARVL |
| International tourism, receipts, current US$ (ST.INT.RCPT.CD) | World Bank — annual country-level tourism receipts | https://data.worldbank.org/indicator/ST.INT.RCPT.CD |
| Country metadata | World Bank — country, region, and income-group classifications | https://api.worldbank.org/v2/country?format=json&per_page=400 |

5. Visualization Justification

A regional grouped bar chart will compare median arrivals recovery with median receipts recovery, making differences between tourism volume and tourism earnings visible. A country-level scatter plot will place arrivals recovery on one axis and receipts recovery on the other, allowing readers to identify countries where earnings and visitor numbers moved in different directions. A time-series line chart will provide the global context needed to interpret both comparisons.

The dashboard will let users filter by region and income group and inspect the underlying country-level observations. This interaction suits a multi-region comparison because it lets the audience move from the overall pattern to specific regional evidence without relying on one summary chart. Every view will include units, source notes, and a short interpretation so that the visuals directly answer the stated research question.

6. Criteria for Success

Data and reproducibility: Both indicators and the metadata source are documented; the download, cleaning, and analysis steps can be rerun from the submitted notebook.

Valid comparison: The baseline, comparison year, inclusion rules, matched-country sample, and missing-data treatment are explicitly reported.

Correct measures: The recovery-index formula is implemented consistently, and regional summaries use an appropriate median or documented aggregation rule.

Clear visual evidence: Charts have descriptive titles, labelled axes, units, source notes, and captions; truncation and colour choices do not exaggerate differences.

Complete interpretation: The final narrative answers the research question and separates evidence from speculative explanations.

Responsible conclusions: Limitations include reporting differences, missing country data, current-US-dollar effects, and the fact that associations are not causal proof.

Functional dashboard: The dashboard runs from the README instructions, filters work correctly, and charts respond without errors.

Submission quality: The Word proposal, notebook, dashboard package, screenshot, and required filenames are complete and checked before submission.

7. Project Collaboration

Division of work

Project coordinator and liaison — He Kejia: Coordinates the project schedule, maintains the shared folder, and liaises with the instructor.

Project scribe — Dong Yushuo: Maintains meeting notes, decisions, and the issue log.

Progress tracker — Dong Yushuo: Tracks weekly milestones and reviews submission completeness.

Shared responsibility: Both members jointly define the analysis, review every output, and prepare the final explanation.

Ground rules

Meet once each week and confirm the next milestone before ending the meeting.

Record major analytical changes in the shared decision log.

Review each other’s code and writing before a deliverable is marked complete.

Keep a shared backup of the notebook and dashboard files.

Resolve disagreements by testing the alternative against the research question and documenting the final choice.

Complete the final package at least 48 hours before the deadline for independent checking.

8. Project Timeline and Deliverables

| Stage | Main activity | Required output |
| --- | --- | --- |
| Week 1 | Confirm topic, question, data sources, indicators, and division of work. | Approved scope and data dictionary |
| Week 2 | Download and clean the data; validate country matches and missing values. | Clean dataset and source log |
| Week 3 | Compute recovery indices; complete exploratory and regional analysis. | Analysis notebook and summary tables |
| Week 4 | Produce static figures and draft the interactive dashboard. | Static figures and dashboard prototype |
| Week 5 | Finish the dashboard, verify reproducibility, document limitations, and assemble files. | Final notebook, dashboard package, README, and QA checklist |

Final deliverables

Revised Pair Project Proposal in Microsoft Word.

Jupyter Notebook with acquisition, cleaning, analysis, and static visualizations.

Cleaned dataset or reproducible download script.

Plotly/Dash dashboard in a correctly named `.zip` file.

Dashboard screenshot and README with environment and run instructions.

Short interpretation of findings, limitations, and next steps.